## INSTRUCTIONS
INSTRUCTIONS
DATE: | 6/4/2006 (UPDATED 6/25/10)
SUBJECT: | RULES FOR USING THIS SET OF SPREADSHEETS
FROM: | THOMAS A. GLASER
1 | USE CAPITAL LETTERS ONLY
2 | DO NOT DELETE COMPLETED OR CANCELLED ITEMS - SORT BY PRIORITY TO BOTTOM OF LIST
3 | HIGHLIGHT IN YELLOW CELLS THAT REQUIRE INPUT
4 | PROCESSING OF TIMING REPORTS AND KTM'S
| a | COPY AND PASTE SUPPLIERS ENTIRE KTM ONTO TAB CORRESPONDING TO MACHINE
| b | COPY SUBSEQUENT KTM'S BELOW PREVIOUS ONES
| c | COPY AND PASTE SPECIAL AS VALUES "CURRENT DUE DATE" COLUMN INTO TIMING SECTION OF MACHINE TAB
| d | CELLS THAT SHOW TIMING CHANGES WILL AUTOMATICALLY HIGHLIGHT IN YELLOW
| e | NOTE REASON FOR TIMING CHANGES IN "HISTORY & CHANGE TRACKING" SECTION
5 | INVESTMENT AND FORECASTING
| a | INITIALLY INSERT A LINE ITEM FOR EACH ITEM WITH A TAB
| b | FILL IN "APPROPRIATED" & "I/O" & "COST BOOK ESTIMATE" CELLS FOR EACH LINE.
NOTE: IF SEVERAL ITEMS SHARE THE SAME I/O THEN ONLY FILL IN THE APPROPRIATED AMOUNT ON ONE ROW
| c | ADD FORMULA TO LINK "TRACKING APPROVED / COMMITTED" CELL TO "PURCHASE TRACKING TOTAL" CELL ON ITEM TABS
| d | RESOLVE ANY OVER SPENT (RED SHADED) APPROPRIATIONS OR LINE ITEMS
| e | FILL IN "UPDATED" CELL
| f | FILL IN "INVOICE DATE CELLS FOR EACH LINE.
| g | FILL IN FORECAST. BY MONTH FOR FIRST TWO YEARS. BY QUARTER FOR NEXT TWO YEARS.
NOTE THESE MAY BE DIRECTLY INPUT OR BY ADDING A FORMULA
| h | RESOLVE ANY MISMATCHED "SUMMARY TO FORECAST CHECK" ITEM (RED SHADED) BY CHANGING FORECAST

## PROGRAM SMMY
PROGRAM SUMMARY
INITIATOR | THOMAS A. GLASER
INITIATED | 2007-10-18
UPDATED | 2008-07-11
PART NAME | ZETA II HVAC MODULE
PLANT | DELPHI LOCKPORT
DEPARTMENT | 847
COLUMN / BAY LOCATION | L47
CUSTOMER | GM
MODEL YEAR | 2010
PROJECT(S) | TH-2095
CN# | N/A
FLOOR SPACE AVAILABLE | SEE KTM
PPAP RUN | 2010-08-02
RUN @ RATE | 2010-08-18
SORP | 2010-11-01
| PROGRAM | PLATFORM | MODEL # | MODEL CODE | DELPHI P/N | CUSTOMER P/N | PLANNING VOLUME | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5 | YEAR 6
MODULE INFORMATION | GMX 511 | ZETA | ACM-140 | C60 | 52423614 | 92197160 | 443 | 326 | 443 | 443 | 443 | 443 | 0
GMX 521
GMX 551
NA
NA
NA
NA
NA
NA
NA
NA
NA
NA
NA
[7 empty] | 443 | 326 | 443 | 443 | 443 | 443 | 0

## MODEL MIX
|  |  | PROGRAM | GMX 353 | J300 | GMX 350 | GMX 353 | GMX 350 | GMX 351 | GMX 351 | J300 | J300 | J300 | E-Flex
EFLEX & J300 4009784 |  |  | PLATFORM | LaCrosse | Cruze | Regal | LaCrosse | Regal | Malibu | Malibu | Cruze | Cruze | Brazil | REFERENCE
E2 & J300 4009650 |  |  | MODEL # | ACM-G649 | ACM-G646 | ACM-G702 | ACM-G654 | ACM-G696 | ACM-G692 | ACM-G682 | ACM-G643 | HVM-G640 | ACM-G646
|  |  | MODEL CODE | C68 | C68 | C68 | CJ2 | CJ2 | CJ2 | C67 | C67 | C42 | C68
|  |  | DELPHI P/N | 5400118 | 5400149 | 16451770 | 5400119 | 16451769 | TBD | TBD | 5400146 | 5400145 | 5400149
|  |  | CUSTOMER P/N | 13 339 551 | 13 345 128 | 13 339 571 | 12 339 550 | 13 339 570 | 20 876 461 | 20 930 881 | 13 337 893 | 13 337 894 | 13345128
FEATURE | PRESENT | CORRECT | FUNCTION
DTM Sensor - Short (Color = Black) | X | X | X | 1 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | SAME AS J300 C68 FOR NA - DIFF SHIP TO LOCATION | 2
DTM Sensor - Long (Color = White) | X | X | X | 1 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 0 |  | 0
Thermistor - Long (Color = White) | X | X | X | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | 1
Sensor Caps in LH Case (Color = White) | X |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 |  | 0
Sensor Caps in RH Case (Color = White) | X |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 3 |  | 0
MODE SEAL | X |  |  | 52420918 | 52420918 | 52420918 | 52420918 | 52420918 | 52420918 | 52420918 | 52420918 |  |  | 52420918
AI SEAL | X | X |  | MOLDED | 16451926 | MOLDED | MOLDED | MOLDED | MOLDED | MOLDED | 16451926 | 16451926 |  | 52420914
FOD | X | X |  | 52427247 | 52427247 | 52427247 | 52427247 | 52427247 | 52427247 | 52427247 | 52427247 | DIFF |  | 52427247
EV CAP | X |  |  | 52432916 | 52432916 | 52432916 | 52432916 | 52432916 | 52432916 | 52432916 | 52432916 | NONE |  | 52432916
TXV STUD | X | X |  | LONG | 52409601 | LONG | LONG | LONG | LONG | LONG | 52409601 | NONE |  | 52409601
HTR PIPE CLAMP | X | X |  | 52423803 | 52423803 | 52423803 | 52423803 | 52423803 | 52423803 | 52423803 | 52423803 |  |  | 52424746
REAR DUCT CASE | X | X |  | REAR | 52420924 | REAR | REAR | REAR | NO REAR | NO REAR | 52420924 | 52420924
HTR PIPE CAPS | X |  |  | 52421793 | 52421793 | 52421793 | 52421793 | 52421793 | 52421793 | 52421793 | 52421793 |  |  | 52421793
MOTOR CAP | X | X |  | NONE | NONE | NONE | NONE | NONE | NONE | NONE | NONE |  |  | 52428308
HTR PIPE | X |  |  | 52426284 | 52426284 | 52426284 | 52426284 | 52426284 | 52426284 | 52426284 | 52426284 |  |  | 52430912
HTR PIPE | X |  |  | 52421792 | 52421792 | 52421792 | 52421792 | 52421792 | 52421792 | 52421792 | 52421792 |  |  | 52430913
TEMP VALVE (SINGLE, DUAL) |  |  | X | SINGLE | SINGLE | SINGLE | DUAL | DUAL | DUAL | SINGLE | SINGLE
MODE VALVE |  |  | X | A | A | A | A | A | A | A | A
AI VALVE(S) |  |  | X | A | A | A | A | A | A | A | A | DIFF W/DIFF CAP CASE, VALVE HELD CLOSED, HOLE CAPPED
MOTOR |  |  | X | A | A | A | A | A | A | A | A | A
LPM / PWM | X | X | X | BOTH LPM PWM LIKE EFLEX TEST | BOTH LPM PWM LIKE EFLEX TEST | BOTH LPM PWM LIKE EFLEX TEST | BOTH LPM PWM LIKE EFLEX TEST | BOTH LPM PWM LIKE EFLEX TEST | BOTH LPM PWM LIKE EFLEX TEST | BOTH LPM PWM LIKE EFLEX TEST | BOTH LPM PWM LIKE EFLEX TEST | BOTH LPM PWM LIKE EFLEX TEST |  | 52432575
MECHANIZATION MODE | X | X |  | (2) Pivot Levers, Mode Cam & Mode Drive Gear | (2) Pivot Levers, Mode Cam & Mode Drive Gear | (2) Pivot Levers, Mode Cam & Mode Drive Gear | (2) Pivot Levers, Mode Cam & Mode Drive Gear | (2) Pivot Levers, Mode Cam & Mode Drive Gear | (2) Pivot Levers, Mode Cam & Mode Drive Gear | (2) Pivot Levers, Mode Cam & Mode Drive Gear | (2) Pivot Levers, Mode Cam & Mode Drive Gear | (2) Pivot Levers, Mode Cam & Mode Drive Gear |  | (2) Mode Cams & (2) Valve Levers
MECHANIZATION AI | X | X |  | (2) Pivot Levers, AI Cam & AI Drive Gear | (2) Pivot Levers, AI Cam & AI Drive Gear | (2) Pivot Levers, AI Cam & AI Drive Gear | DIRECT DRIVE (2) | DIRECT DRIVE (2) | DIRECT DRIVE (2) | (2) Pivot Levers, AI Cam & AI Drive Gear | (2) Pivot Levers, AI Cam & AI Drive Gear | NONE |  | (2) Pivot Levers, AI Cam & AI Drive Gear
FILTER |  |  |  | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST |  | NOT INSP IN TEST
SPLITTER WALL |  |  |  | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST | NOT INSP IN TEST |  | NOT INSP IN TEST
LABEL | X | X |  | SCAN | SCAN | SCAN | SCAN | SCAN | SCAN | SCAN | SCAN | SCAN |  | SCAN
WIRE HARNESS | X | SCAN | X | A & B | A & B | A & B (SAME AS GMX 353 C68 EXCEPT FOR LENGTH) | A & C | A & C (SAME AS GMX 353 CJ2 EXCEPT FOR LENGTH) | A & C (SAME AS GMX 353 CJ2 EXCEPT FOR LENGTH) | A | A | DIFF
DRAIN ORIENTATION | X | X | X | A | A | A | A | A | A | A | A | CAPPED |  | B

## PROGRAM KTM
| Level 2 | Continuous Improvement KTM (Key Task Monitor) | [51 empty] | Continuous Improvement KTM (Key Task Monitor) | [51 empty] | Continuous Improvement KTM (Key Task Monitor)
| Project Started : 1/7/07 | Project Description : | [6 empty] | ZETA II HVAC MODULE | [44 empty] | Project Description : | [6 empty] | ZETA II HVAC MODULE | [44 empty] | Project Description : | [6 empty] | ZETA II HVAC MODULE
| Proposal Produced : 10/16/07 | [7 empty] | Develop & Validate Production Cell | [51 empty] | Develop & Validate Production Cell | [51 empty] | Develop & Validate Production Cell
| Key Activity | 1st Quarter 2007 | [12 empty] | 2nd Quarter 2007 | [12 empty] | 3rd Quarter 2007 | [12 empty] | 4th Quarter 2007 | [12 empty] | 1st Quarter 2008 | [12 empty] | 2nd Quarter 2008 | [12 empty] | 3rd Quarter 2008 | [12 empty] | 4th Quarter 2008 | [12 empty] | 1st Quarter 2009
| Week no. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  | Completion Date
| Month | JA | JA | JA | JA | JA | FE | FE | FE | FE | MR | MR | MR | MR | AP | AP | AP | AP | MY | MY | MY | MY | MY | JN | JN | JN | JN | JL | JL | JL | JL | JL | AU | AU | AU | AU | SE | SE | SE | SE | OC | OC | OC | OC | OC | NO | NO | NO | NO | DE | DE | DE | DE | JA | JA | JA | JA | JA | FE | FE | FE | FE | MR | MR | MR | MR | MR | AP | AP | AP | AP | MY | MY | MY | MY | JN | JN | JN | JN | JN | JL | JL | JL | JL | AU | AU | AU | AU | AU | SE | SE | SE | SE | OC | OC | OC | OC | NO | NO | NO | NO | NO | DE | DE | DE | JA | JA | JA | JA | JA | FE | FE | FE | FE | MR | MR | MR | MR | Responsible | Plan | Actual
A | Month: PROGRAM COMPOSITE |  | 2009-02-16
| Month: EQUIPMENT | GLASER | 2008-05-09
| Month: TOOLING & GAGES | GLASER | 2008-05-09
| Month: EXPENSE | BERG | 2008-05-09
| INTEGRATION | [41 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | [46 empty] | GLASER/BERG | 2008-06-06
| INSTALLATION | [117 empty] | GLASER/BERG | 2008-06-27
| DOCUMENTATION | [117 empty] | GLASER/BERG | 2008-07-25
| VALIDATION | [117 empty] | GLASER/BERG | 2008-07-25
| PVV UNITS DUE (7/11/08) BENCH BUILT | [117 empty] | GLASER/BERG | 2008-07-11
| PPAP PARTS REQUIRED (7/24/08 - 7/30/08) | [117 empty] | GLASER/BERG | 2008-07-30
| SUBMIT FULL PPAP (9/18/08) | [117 empty] | GLASER/BERG | 2008-09-18
| ZDL (9/18/08 - 11/28/08) | [117 empty] | GLASER/BERG | 2008-11-28
| CUSTOMER RUN @ RATE (11/20/08 - 11/28/08) | [117 empty] | GLASER/BERG | 2008-11-28
| SOP (2/16/09) | [117 empty] | GLASER/BERG | 2009-02-16
B | EQUIPMENT | [118 empty] | 2008-07-15
1 | Stations & Controls - Specification | [117 empty] | GLASER | 2007-11-09 | bar: 5 to 8
2 | Stations & Controls - RFQ/Quotations | [117 empty] | GLASER | 2007-12-07 | bar: 6 to 9
3 | Stations & Controls - Issue PO | [117 empty] | GLASER | 2007-12-21 | bar: 9 to 13
4 | Stations & Controls - Design | [117 empty] | GLASER | 2008-02-01 | bar: 11 to 29
[57 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
5 | Stations & Controls - RFQ/Quotations | [117 empty] | GLASER | 2007-12-07 | bar: 9 to 12
6 | Stations & Controls - Issue PO | [117 empty] | GLASER | 2007-12-21 | bar: 9 to 12
7 | Stations & Controls - Build | [117 empty] | GLASER | 2008-06-30 | bar: 13 to 15
[69 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
8 | Heater Clinch & Test (HCT) - Specification | [117 empty] | GLASER | 2007-10-19
9 | Heater Clinch & Test (HCT) - RFQ/Quotations | [117 empty] | GLASER | 2007-11-09
10 | Heater Clinch & Test (HCT) - Issue PO | [117 empty] | GLASER | 2007-11-23
11 | Heater Clinch & Test (HCT) - Design | [117 empty] | GLASER | 2008-01-04
12 | Heater Clinch & Test (HCT) - Build | [117 empty] | GLASER | 2008-06-05
[56 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
13 | Heater Clinch & Test (HCT) - Machine Qualification | [117 empty] | GLASER | 2008-06-18 | bar: 11 to 21
14 | Flame Braze - Specification | [117 empty] | GROVER | 2007-10-26 | bar: 2 to 5
15 | Flame Braze - RFQ | [117 empty] | GROVER | 2007-11-09
16 | Flame Braze - Issue PO | [117 empty] | GROVER | 2008-03-02 | bar: 7 to 8
17 | Flame Braze - Design | [117 empty] | GROVER | 2008-04-14 | bar: 9 to 14
18 | Flame Braze - Build | [117 empty] | GROVER | 2008-07-15
[50 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
19 | Flame Braze - Debug / Run Parts | [117 empty] | GROVER | 2008-07-15 | bar: 17 to 19
20 | Mass Spec - Specification - new | [117 empty] | GROVER | 2007-11-07
21 | Mass Spec - Issue PO | [117 empty] | GROVER | 2008-03-20 | bar: 1 to 2
22 | Mass Spec - Build | [117 empty] | GROVER | 2008-07-15
[50 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
23 | Mass Spec - Debug / Run Parts | [117 empty] | GROVER | 2008-07-15 | bar: 3 to 12; 15 to 17
24 | Press Balancer - Specification | [117 empty] | GLASER | 2007-10-19
25 | Press Balancer - RFQ/Quotations | [117 empty] | GLASER | 2007-11-09
26 | Press Balancer - Issue PO | [117 empty] | GLASER | 2007-11-23 | bar: 1 to 2
27 | Press Balancer - Design | [117 empty] | GLASER | 2008-01-04 | bar: 1 to 11
28 | Press Balancer - Build | [117 empty] | GLASER | 2008-04-11 | bar: 1 to 8
[55 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 18
29 | Press Balancer - Machine Qualification | [117 empty] | GLASER | 2008-05-02 | bar: 15 to 18
30 | Welder - Specification | [117 empty] | GLASER | 2007-10-19
31 | Welder - RFQ/Quotations | [117 empty] | GLASER | 2007-11-09
32 | Welder - Issue PO | [117 empty] | GLASER | 2007-11-23
33 | Welder - Design | [117 empty] | GLASER | 2008-01-04 | bar: 3 to 8
34 | Welder - Build | [117 empty] | GLASER | 2008-04-11
[57 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
35 | Welder - Machine Qualification | [117 empty] | GLASER | 2008-05-02
36 | Tester - Specification | [117 empty] | GLASER | 2007-10-19
37 | Tester - RFQ/Quotations | [117 empty] | GLASER | 2007-11-09
38 | Tester - Issue PO | [117 empty] | GLASER | 2007-11-23
39 | Tester - Design | [117 empty] | GLASER | 2008-01-04
[55 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Updated Timeline | bar: 9
3/7 | bar: 9
Design Review - Fixed Sensors / Cap & Seal Probe | bar: 10
3/12 | bar: 10
Detail & Release Approved Items | bar: 10 to 12
3/12-3/17 | bar: 10 to 12
Design review - LPM Probe | bar: 11 to 13
3/17 | bar: 11 to 13
Detail & Release Approved Items | bar: 12 to 14
3/18-3/21 | bar: 12 to 13
Design Harness Connection | bar: 12 to 14
3/18-3/21
Detail & Release Approved Items | bar: 13 to 16
3/24-3/28 | bar: 13 to 16
Detail Pneumatic Curcuit | bar: 13 to 16
3/25-3/28 | bar: 13 to 16
Delphi Design Approval | bar: 16
4/21-4/24 | bar: 16
40 | Tester - Build | [117 empty] | GLASER | 2008-04-11
Order Materials | bar: 10 to 16
3/12-4/4 | bar: 16
Manufacture | bar: 11 to 16
3/19-5/9
Assembly
5/2-5/16
Tester - Ready to Program
5/19-5/23
41 | Tester - Machine Qualification | [117 empty] | GLASER | 2008-05-02
42 | PACK SYSTEM - Specification | [117 empty] | GLASER | 2007-11-09
43 | PACK SYSTEM - RFQ/Quotations | [117 empty] | GLASER | 2007-11-30
44 | PACK SYSTEM - Issue PO | [117 empty] | GLASER | 2007-12-14
45 | PACK SYSTEM - Design | [117 empty] | GLASER | 2008-01-18 | bar: 1 to 7
46 | PACK SYSTEM - RFQ/Quotations | [117 empty] | GLASER | 2007-11-30 | bar: 8 to 9
47 | PACK SYSTEM - Issue PO | [117 empty] | GLASER | 2007-12-14 | bar: 10 to 11
48 | PACK SYSTEM - Build | [117 empty] | GLASER | 2008-03-07
[72 empty] | 7 | 8 | 9 | 10 | 11 | 12 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
49 | PACK SYSTEM - Machine Qualification | [117 empty] | GLASER | 2008-03-14
50 | Pack Area & Hoist | [117 empty] | GLASER | 2008-04-04
(also Validate Pack)
51 | Xycam Build Order System | [117 empty] | GLASER | TBD
C. | TOOLING & GAGES | [118 empty] | 2008-07-18
52 | Assembly Fixtures - Specification | [117 empty] | GLASER | 2007-11-02
53 | Assembly Fixtures - RFQ/Quotations | [117 empty] | GLASER | 2007-11-23
54 | Assembly Fixtures - Issue PO | [117 empty] | GLASER | 2007-12-07
55 | Assembly Fixtures - Design | [117 empty] | GLASER | 2007-12-28
56 | Assembly Fixtures - Build | [117 empty] | GLASER | 2008-03-21
[52 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 12 | 12 | 12 | 16
57 | Assembly Fixtures - RFQ/Quotations | [117 empty] | GLASER | 2008-04-11 | bar: 9 to 12
58 | Assembly Fixtures - Issue PO | [117 empty] | GLASER | 2008-04-25 | bar: 11 to 16
59 | Assembly Fixtures - Build | [117 empty] | GLASER | 2008-07-18 | bar: 12 to 16
[64 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 9 | 12 | 13
60 | Gages | [117 empty] | GLASER | TBD
(Htr Pipe, Evap, Mtr Gap, Torque, End Point, DTM)
D. | EXPENSE | [118 empty] | 0
61 | Finalize Purchased Part Packaging | [117 empty] | Amara | TBD
BERG
62 | Order Parts for Equipment & Creform Tryouts | [117 empty] | PCL | TBD
Amara
63 | Develop Creform Concepts | [117 empty] | BERG | TBD
64 | Subcontract Design of Drawings for Creform | [117 empty] | Contractor | TBD
BERG
65 | RFQ & Order Creform | [117 empty] | BERG | TBD
66 | Build & Validate Creform | [117 empty] | Contractor | TBD
| (use Work Station & Fixture for Debug) | [117 empty] | BERG
67 | Order 14 Label Machines | [117 empty] | GLASER | TBD
(2) Mass Spec, (2) Balancer
68 | Order Misc Equipment | [117 empty] | GLASER | TBD
(Tool Cab, Trash Cans, Scrap Bins, etc…)
E. | INTEGRATION | [118 empty] | 0
69 | Update MSD (Workshop) | [117 empty] | GLASER/BERG | TBD
70 | Complete Cell Layout Drawing | [117 empty] | BERG | TBD
(Ergo & Safety Review)
71 | Complete WorkSmart Plan Views | [117 empty] | TBD | TBD
72 | RFQ & Place Order for Cell | [117 empty] | GLASER | TBD
73 | Order Workstation for Creform Debug | [117 empty] | Contractor | TBD
| (Including Fixture) | [117 empty] | BERG
74 | Install Equipment & Creform in Cell | [117 empty] | Contractor | TBD
GLASER/BERG
H | INSTALLATION | [118 empty] | 0
75 | Update & Dimension Plant & Cell Layout | [117 empty] | BERG | TBD
(Including Material Storage & Movement)
76 | Clear Area for Cells & Material Storage | [117 empty] | TBD | TBD
(Paint Floor Lines)
77 | Run Electric Drops for Cell Equipment | [117 empty] | TBD | TBD
78 | Setup Supermarket & Material Movement | [117 empty] | TBD | TBD
(Tuggers, Mtrs, Fans, Htrs, Evaps & Plastic)
79 | Photo Document Cell | [117 empty] | BERG | TBD
80 | Tag & Move Cell to Vandalia | [117 empty] | GLASER | TBD
| (Move Orders) | [117 empty] | BERG
F. | DOCUMENTATION | [118 empty] | 0
81 | Develop PFMEA, PFD, PCP | [117 empty] | BERG | TBD
82 | Complete PP-024 for Production Readiness | [117 empty] | BERG | TBD
83 | Develop PC&L Plan / PFEP | [117 empty] | BERG | TBD
Amara
84 | Develop Operator Instr / Insp Check sheets | [117 empty] | BERG | TBD
(Model Change Check sheet)
85 | Develop Standard Operating Sheets | [117 empty] | BERG | TBD
86 | Attend DFM / DFA Workshop | [117 empty] | BERG | TBD
| in Luxembourg | [117 empty] | GLASER
87 | Update MSD | [117 empty] | BERG | TBD
GLASER
88 | Develop EP Recipes in Nematron | [117 empty] | BERG | TBD
Sada
89 | Develop & Post Equip Lockout Placards | [117 empty] | GLASER | TBD
90 | Develop Equip Audit Plans, Bogeys, Setup | [117 empty] | GLASER/BERG | TBD
Procedures and JI's to Run Equipment
91 | Develop Equip PM & Spare Parts List | [117 empty] | GLASER | TBD
G | VALIDATION | [118 empty] | 0
92 | Order 350 Parts (100 pc Capability Study) | [117 empty] | PCL | TBD
93 | Input EP Recipes in Nematron | [117 empty] | BERG | TBD
Sada
94 | Develop Bogeys for EP & Equip Checks | [117 empty] | GLASER | TBD
BERG
95 | Debug & Validate Creform in Cell | [117 empty] | BERG | TBD
96 | Debug & Validate Equipment in Cell | [117 empty] | GLASER | TBD
BERG
97 | Conduct MSA's on Equipment & Cell | [117 empty] | GLASER | TBD
BERG
98 | Validate Finished Module Pack | [117 empty] | GLASER | TBD
BERG
| Key: | [8 empty] | Comments | [103 empty] | Comments
| Plan (blue) |  |  | Revised Plan | [103 empty] | Revised Plan
Actual (green)
| Off Plan (red) |  |  |  | Milestone | [103 empty] | Milestone
Current Week

## $ SUMMARY
PROJECT SUMMARY | [7 empty] | Capital Forecast ($000)
TH-2095 | [6 empty] | Check +/- Tolerance | TH-2095
ZETA II HVAC MODULE | [6 empty] | 500 | ZETA II HVAC MODULE
ZETA | [7 empty] | ZETA
[9 empty] | UPDATED | 1899 | [11 empty] | 1900 | [11 empty] | 1901 | [11 empty] | 1902
| APPROPRIATED | I/O # | COST BOOK ESTIMATE | TRACKING APPROVED / COMMITTED | ANTICIPATED SPENDING | REMAINING | SUMMARY TO FORECAST CHECK |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | TOTAL ALL YEARS
GRAND TOTAL | 0 |  | 0 | 0 | 0 | 0 | OK | GRAND TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EQUIPMENT | 0 |  | 0 | 0 | 0 | 0 | OK | EQUIPMENT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOOLING | 0 |  | 0 | 0 | 0 | 0 | OK | TOOLING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EXPENSE | 0 |  | 0 | 0 | 0 | 0 | OK | EXPENSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MOLD TOOLING | 0 | 0 | 0 | 0 | 0 | 0 | OK | MOLD TOOLING |  | 1899 1: 0 | 0
EQUIPMENT (TH2095) | 0 |  | 0 | 0 | 0 | 0 | OK | EQUIPMENT (TH2095) | Invoice Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STATIONS & CONTROLS | [5 empty] | 0 | OK | STATIONS & CONTROLS | [49 empty] | 0
HEATER CLINCH & TEST (HCT) | [6 empty] | OK
FLAME BRAZE | [6 empty] | OK
MASS SPEC | [6 empty] | OK
PRESS BALANCER | [6 empty] | OK
WELDER | [6 empty] | OK
TESTER | [6 empty] | OK
OK
OK
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
TOOLING (TH2095) | 0 |  | 0 | 0 | 0 | 0 | OK | TOOLING (TH2095) | Invoice Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FIXTURE | [5 empty] | 0 | OK | FIXTURE | [49 empty] | 0
EV SEAL ASSEMBLY FIXTURE | [6 empty] | OK
HEATER SEAL ASSEMBLY FIXTURE | [6 empty] | OK
OK
OK
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
EXPENSE (TH2095) | 0 |  | 0 | 0 | 0 | 0 | OK | EXPENSE (TH2095) | Invoice Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REARRANGEMENT | [5 empty] | 0 | OK | REARRANGEMENT | [49 empty] | 0
RUN OFF PARTS | [6 empty] | OK
OK
OK
OK
OK
OK
OK
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
MOLD TOOLING (TH2095) | 0 |  | 0 | 0 | 0 | 0 | OK | MOLD TOOLING (TH2095) | Invoice Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
[6 empty] | 0 | OK | 0 | [49 empty] | 0
HIGHLIGHTED CELLS REQUIRE INPUT AT UPDATE

## T&E TRACKER
TOOLING & EQUIPMENT TRACKER
COMMON NAME | STATIONS & CONTROLS | SNAP AUDIT GAGE
PRIORITY | 1 | 1
QUANTITY | 1 | 1
CURRENT T OR E AVAILABLE (Y/N) | Y | N
LAST DATE TO INITIATE SPECIFICATION | PAST DUE | PAST DUE
DESIGN INSIDE / OUTSIDE | OUTSIDE | OUTSIDE
BUILD INSIDE / OUTSIDE | INSIDE | OUTSIDE
PROJECT # | 1926 | 1926
FACILITIES I/O# | 600 041 640 / 600 041 644 | NA
TOOLING I/O# | NA | 610 051 366
RE-BILLABLE (Y/N)? | NA | NA
EXPENSE I/O# | 630 033 383 / 630 033 387 / 630 033 388 | NA
JOB NUMBER(S) | 43026, 44021 | 44132
TOOL NUMBER(S) | 4009663.001 | 9104349.001
RFQ # | DSR 1855 | NR
DELPHI ME DESIGNER | BURKHARDT, D. | BURKHARDT, D.
DELPHI CE DESIGNER | GOFF, K. | NR
DELPHI ME | GLASER, T. | GLASER, T.
DELPHI CE | SADA, H. | NR
SUPPLIER | VOSS
PROJECT MANAGER | LUTE, PETE
ME SUPPLIER | LUTE, PETE
CE SUPPLIER | SADA, H.
LEAD MAN SUPPLIER | NA
INSTALLER | DELPHI | DELPHI
ASSET NUMBER / AUC | J2 6014 668 | NR
DESCRIPTION / COMMENTS | NONE | NONE
. |  |  | .
ACTUAL HISTORICAL DATES & INFORMATION
TOOL CARD REQUEST | 2008-12-11 | 2009-05-14
UNION REQUEST / NOTIFICATION
INSIDE / OUTSIDE DECISION
SCHEDULE TIMING REPORTS IN OUTLOOK (1ST & 15TH)
DBS ME 3.9.4 PLAN APPROVED
ASSET TAG VERIFIED AFFIXED
RECEIVED DATE
PARTIAL INVOICE SIGNED & SUBMITTED FOR PAYMENT
SAFETY TAGGED DATE
SAFETY APPROVAL DATE
LOCKOUT PLACARD DATE
MSA COMPLETE
CALIBRATION & SET-UP TOOLS / BOGEYS INSPECTED & IN GAGE CONTROL
OUTSTANDING ITEMS FROM TAB VERIFIED COMPLETE
DOCUMENTATION DELIVERED TO PML & FILED (SEE DOCUMENT SUMMARY TAB)
APPLICATION PROGRAMS FILED
SPARES IN INDIRECT SYSTEM & ORDERED
PM & SERVICE JI'S SUBMITTED DATE
DOCUMENTS UPDATED & HARDCOPY AT OPERATIONS
SERVICE PERSONNEL TRAINED TO DOCUMENTS
DBS ME 3.9.4 APPROVED DATE
FINAL INVOICE SIGNED & SUBMITTED FOR PAYMENT
CLOSE / TRANSFER I/O $
. |  |  | .

## DOCUMENT SMMY
MACHINE & TOOL DOCUMENT DIRECTORY
KEY
REQUIRES INPUT
UNSUBMITTED
INITIAL SUBMISSION RECEIVED
"RED LINES" BEING UPDATED
APPROVAL SUBMISSION RECEIVED
FILED
IN REVISION AFTER FILING
NOT REQUIRED | NR
NOTE: FULL FILE NAMES MUST BE FILLED IN
DESCRIPTION | CLASS (C, T, E) | ENGINEER RESPONSIBLE | MECHANICAL MODEL | MECHANICAL NATIVE 2D | MECHANICAL ACAD 2D | MECHANICAL BM | CONTROLS 2D | CONTROLS BM | CONTROLS PROGRAMS | AUDIT / USE INSTRUCTION (II, MS, VA) | SERVICEMAN (JI) | BOGEYS (JI) | CHECK SHEETS (CS) | SET UP (ES) | LOCKOUT (LO) | RISK ASSESSMENT | SUPPLIER’S SOUND DATA FORM and CERTIFICATION SHEET (SL-1 APPENDIX F) | SAFETY CIRCUIT CERTIFICATION (SCC) | ERGONOMICS CHECKLIST(S) | MSA | Health & Safety Checklist (DS3260) | MSDS | MACHINE REFERENCE DOCUMENTS
STATIONS & CONTROLS | C | DUQUETTE
STATION 10 | C | DUQUETTE
STATION 20 | C | DUQUETTE
STATION 30 | C | DUQUETTE
STATION 40 | C | DUQUETTE
STATION 50 | C | DUQUETTE
STATION 60 | C | DUQUETTE
STATION 70 | C | DUQUETTE
STATION 80 | C | DUQUETTE
STATION 90 | C | DUQUETTE
STATION 100 | C | DUQUETTE
STATION 110 | C | DUQUETTE
STATION 120 | C | DUQUETTE
AUTO TRANSFER CART | C | DUQUETTE
TEARDOWN STATION | C | DUQUETTE
COMPUTER ASSEMBLY | C | DUQUETTE
DEVICE NET POWER SUPPLY ASSEMBLY | C | DUQUETTE
24 VDC POWER SUPPLY ASSEMBLY | C | DUQUETTE
AUXILIARY 120 VAC POWER DISCONNECT | C | DUQUETTE
AUXILIARY 120 VAC POWER OUTLET | C | DUQUETTE
MINOMI - UPPER EVAP | C | DUQUETTE
MINOMI - LOWER EVAP | C | DUQUETTE
FIXTURE RACK | E | DUQUETTE
EXPAND FOR STANDS, CHUTES, CARTS, RAILS, TABLES | E | DUQUETTE
TEAR DOWN TABLE | E | DUQUETTE
DEPARTMENT SIGN | E | DUQUETTE
ADDRESS SIGNS | E | DUQUETTE
ANDON SIGN | E | DUQUETTE
PRODUCTION STATUS BOARD | E | DUQUETTE
EV FIXTURE | T | DUQUETTE
UPPER CASE FIXTURE | T | DUQUETTE
PRESS BALANCER | C | GLASER
HEATER CLINCH & TEST (HCT) | C | GLASER
WELDER | C | GLASER
TESTER | C | GLASER
PACK SYSTEM | C | GLASER
LIFT ASSIST | C | GLASER
CONTAINMENT TEST | C | GLASER
CONTAINMENT TEST - LPM CONNECTOR | T | GLASER
CONTAINMENT TEST - HARNESS CONNECTOR | T | GLASER
PORTABLE LEAK TEST (PLT) | C | GLASER
INTERNAL TUBE CONNECTOR | T | GLASER
EXTERNAL TUBE CONNECTOR | T | GLASER
HOIST HOLSTER | T | GLASER
FIXTURES | T | GLASER
FAN PRESS ALIGNMENT GAGE | T | GLASER
FAN PRESS FORCE GAGE | T | GLASER
FAN MASTER 150MM (HI EFFICIENCY) | T | GLASER
HEATER CLINCH GAP GAGE (2MM) | T | GLASER
HEATER CLINCH GAP GAGE - THICK | T | GLASER
HOLD DOWN HEIGHT GAGE | T | GLASER
LIFT ASSIST TOOL | T | GLASER
PACK LIFT TOOL | T | GLASER
CART HOLD DOWN | T | GLASER
ACTUATOR RESET TOOL | T | GLASER
TEMPERATURE SENSOR ASSEMBLY TOOL | T | GLASER
END POINT GAGE | T | GLASER
DRAIN PROBE | T | GLASER
FAN REMOVER | T | GLASER
FAN PULLER | T | GLASER
FLAME BRAZE | C | GROVER
MASS SPEC | C | GROVER
FLAME BRAZE FIXTURE | T | GROVER
MASS SPEC FIXTURE | T | GROVER
FLAME BRAZE END POINT GAGE | T | GROVER
JOB INSTRUCTION HOLDER | E | REFERENCE
FOOT | T | REFERENCE
STRAIGHT TRACK JOINER | T | REFERENCE
RFID BRACKET | T | REFERENCE
END CAP | T | REFERENCE
CART STOP | T | REFERENCE
FAN MASTER COLLET | T | REFERENCE
FAN MASTER SHAFT | T | REFERENCE
FAN MASTER WEIGHTS | T | REFERENCE
FAN MASTER WEIGHT ASSEMBLY TOOL | T | REFERENCE
SOCKET MAGNET FORCE GAGE | T | REFERENCE

## EXAMPLE ITEM
T/E NAME: | STATIONS & CONTROLS
T/E #: | 4009498 / 5009498
PURCHASE TRACKING
DATE WRITTEN | PR # | I/O # | ITEM (INCLUDE QTY IF MULTIPLE) | AMOUNT | PO # | DATE ISSUED | SUPPLIER | STATUS | COMMENTS | INVOICE # | INVOICE APP'D DATE
2006-05-25 | 39487 | 600 038 593 | (1) S&C | 117000 | 450 426 297 | 2006-06-06 | CARDINAL | 38944 | 061012 QUOTE CARDINAL ATC BRAKE DEL-101206-01-DB | AAAAAAA | MM/DD/YY
2006-05-25 | 39487 | 601 038 593 | PARTS | 25450 | 450 426 297 | 2006-06-06 | CARDINAL | 38944 | 061006 QUOTE DEL-100606-01-DB-REV01 (Changes).pdf
2006-05-25 | 39487 | 602 038 593 | HOLD BACK | 13000 | 450 426 297 | 2006-06-06 | CARDINAL | 38944 | 061026 QUOTE CREFORM DEL-102606-01-DB (VANDALIA).pdf
2006-06-28 | 39456 | 603 038 593 | PARTS | 20390.97 | 450 426 297 | 2006-06-29 | CARDINAL | 38944 | QUOTE #NY01-285497
TOTAL |  |  |  | 175840.97
TIMING TRACKING
| QUOTED TIMING | 2008-07-01 | 2008-07-15 | 2008-08-01 | 2008-08-15 | 2008-09-01 | DATE | DATE | DATE
PRODUCT DATA | 2008-07-03 | 2008-07-03 | 2008-07-03 | 2008-07-03 | 2008-07-03 | 2008-07-03 | MM/DD/YY | MM/DD/YY | MM/DD/YY
SPECIFICATION | 2008-05-30 | 2008-05-30 | 2008-05-30 | 2008-05-30 | 2008-05-30 | 2008-05-30
RFQ | 2008-06-11 | 2008-06-11 | 2008-06-11 | 2008-06-11 | 2008-06-11 | 2008-06-11
PR | 2008-06-20 | 2008-06-20 | 2008-06-20 | 2008-06-20 | 2008-06-20 | 2008-06-20
PO | 2008-06-26 | 2008-06-26 | 2008-06-26 | 2008-06-26 | 2008-06-26 | 2008-06-26
SAMPLE PARTS | 2008-07-03 | 2008-07-03 | 2008-07-03 | 2008-07-03 | 2008-07-03 | 2008-07-03
KICK OFF |  | 2008-07-04 | 2008-07-04 | 2008-07-04 | 2008-07-04 | 2008-07-04
DESIGN MECHANICAL |  | 2008-07-18 | 2008-07-18 | 2008-07-18 | 2008-07-18 | 2008-07-18
DESIGN ELECTRICAL |  | 2008-07-18 | 2008-07-18 | 2008-07-18 | 2008-07-18 | 2008-07-18
DESIGN PNEUMATICS |  | 2008-07-18 | 2008-07-18 | 2008-07-18 | 2008-07-18 | 2008-07-18
RISK ASSESSMENT |  | 2008-07-11 | 2008-07-11 | 2008-07-11 | 2008-07-11 | 2008-07-11
CONCEPT APPROVAL |  | 2008-07-11 | 2008-07-11 | 2008-07-11 | 2008-07-11 | 2008-07-11
MODEL / PLAN APPROVAL |  | 2008-07-18 | 2008-07-18 | 2008-07-18 | 2008-07-18 | 2008-07-18
DETAIL MECHANICAL APPROVAL |  | 2008-07-18 | 2008-07-18 | 2008-07-19 | 2008-07-19 | 2008-07-19
CONTROLS APPROVAL |  | 2008-07-18 | 2008-07-18 | 2008-07-18 | 2008-07-18 | 2008-07-18
PROCURE MECHANICAL |  | 2008-08-01 | 2008-08-01 | 2008-08-01 | 2008-08-01 | 2008-08-01
PROCURE ELECTRICAL |  | 2008-08-01 | 2008-08-01 | 2008-08-01 | 2008-08-01 | 2008-08-01
PROCURE PNEUMATICS |  | 2008-08-01 | 2008-08-01 | 2008-08-01 | 2008-08-01 | 2008-08-01
MANUFACTURE PARTS |  | 2008-08-15 | 2008-08-15 | 2008-08-15 | 2008-08-15 | 2008-08-16
CONTROLS ASSEMBLY |  | 2008-08-08 | 2008-08-08 | 2008-08-08 | 2008-08-08 | 2008-08-08
FINAL ASSEMBLY |  | 2008-08-15 | 2008-08-15 | 2008-08-15 | 2008-08-15 | 2008-08-15
DEBUG MECHANICAL & RING OUT |  | 2008-08-22 | 2008-08-22 | 2008-08-22 | 2008-08-22 | 2008-08-22
PROCURE RUN OFF PARTS |  | 2008-08-08 | 2008-08-08 | 2008-08-08 | 2008-08-08 | 2008-08-08
LOAD PROGRAM & DEBUG SYSTEM |  | 2008-08-22 | 2008-08-22 | 2008-08-22 | 2008-08-22 | 2008-08-22
QUALIFICATION |  | 2008-09-12 | 2008-09-12 | 2008-09-12 | 2008-09-12 | 2008-09-12
SHIP | 2008-08-21 | 2008-09-12 | 2008-09-12 | 2008-09-12 | 2008-09-12 | 2008-09-12
INSTALLATION |  | 2008-09-19 | 2008-09-19 | 2008-09-19 | 2008-09-19 | 2008-09-19
QUALIFICATION |  | 2008-09-26 | 2008-09-26 | 2008-09-26 | 2008-09-26 | 2008-09-26
HISTORY & CHANGE TRACKING
|  | Priority | 0 | 1 | 2 | 3 | 4 | CONTROLS, MECHANICAL, OR 5 IF DOCUMENTS VERIFIED
|  | Meaning | Safety | No Build Production / Quality Issue | Hinders Production But Does Not Stop It / Minor Quality Issue | General Working Environment | Continuous Improvement | Complete
DATE ADDED | ITEM | QUOTE REQUIRED (Y/N)? | DESCRIPTION | AMOUNT | PO EFFECT (INCREASE, DECREASE, NO-CHANGE) | DELPHI ACCEPTED? (Y/N) | RESPONSIBLE | STATUS | PRIORITY
2006-10-17 | 5 | Y | ATC - CART TILTS WHEN FIXTURE IS LOADED - ADD ANTI-TILT DETAILS |  | INCREASE |  | BENDER | FEATURES TO BE ADDED TO LAG TO FLOOR AT INSTALLATION | 0
2006-10-03 | 23 | N | WIP - RIVET END CAPS ON |  | NO-CHANGE |  | BENDER | ONGOING | 0
2006-10-09 | 1 | Y | ATC - STOP BYPASS - TARGET MANUAL RELEASE SO THAT STOP MAY BE USED TO HOLD CART IN PLACE WHILE FIXTURE IS LOAD/UNLOADING | 420 | INCREASE | Y - 061012 QUOTE CARDINAL ATC BRAKE DEL-101206-01-DB | BENDER | PNEUMATIC FOOT VALVES TO BE USED IN PLACE OF SOLENOID VALVES | 1
2006-09-21 | 13 | N | GENERAL - RED SCRAP BINS (4) |  | NO-CHANGE |  | MYERS |  | 1
2006-10-17 | 3 | N | 010 - DIFFICULTY ASSEMBLING LEVERS & CAMS |  | NO-CHANGE |  | MYERS |  | 2
2006-10-17 | 2 | N | 040 - DIFFICULTY IN PICKING HEATER FOAM - SOLUTION? |  | NO-CHANGE |  | DUQUETTE |  | 2
2006-10-04 | 4 | Y | 070 - FIX / BUY PARTS FOR LABEL MACHINES |  | INCREASE |  | BENDER | NOT ASSEMBLED DURING 11/1 VISIT | 2
2006-10-18 | 1 | N | 090 - SOUND ROOM CART AND FIXTURE |  | NO-CHANGE |  | BENDER |  | 2
2006-10-16 | 5 | N | 090 - STATION LIGHT |  | NO-CHANGE |  | BENDER | ONE BILB NOT LIGHTING AT 11/1 VISIT | 3
2006-06-26 | 53 | Y | GENERAL -SCANNERS - 4 OF 4 SENT BUT REQUIRE REPAIR - BUY 4 NEW ONES |  | INCREASE |  | DUQUETTE |  | 3
2006-10-03 | 8 | N | 040 - SCANNER TARGET |  | NO-CHANGE |  | MYERS | POSTPONE UNTIL BALANCER | 4
2006-10-03 | 7 | N | 040 - UNIT HITS SEALS - NO ACTION AT THIS TIME |  | NO-CHANGE |  | DUQUETTE | HOW DOES ADRIAN HAVE PARTS PRESENTED | 4
2006-10-03 | 12 | N | GENERAL - ADD LABELS TO OIB'S PER PRINT - ADHESIVE BACKED |  | NO-CHANGE |  | GLASER | FEED BACK TO VENDOR | 4
2006-06-07 | 1 | N | GENERAL - improved stop design |  | NO-CHANGE |  | GLASER | PROTOTYPE DUE 12/7 | 4
2006-09-21 | 12 | N | GENERAL - TRASH BINS - 25, 30, 40, 70 |  | NO-CHANGE |  | MYERS |  | 4
2006-10-04 | 2 | N | PC - ES DOC - START TEST B4 PC |  | NO-CHANGE |  | GLASER |  | 4
COMPLETE
2006-09-12 | 6 | N | PC - STRAP DOWN UPS |  | NO-CHANGE |  | BENDER |  | 5
2006-10-04 | 12 | N | SET UP TEARDOWN STATION |  | NO-CHANGE |  | BENDER | RUBBER FOR TOP | 5
2006-09-26 | 4 | N | PC - TOUCH UP ORANGE ON PANEL DOOR - COVER HOLES |  | NO-CHANGE |  | BENDER | REVIEW 10/3 | 5
2006-06-07 | 11 | N | WIP - Creform - Obtain design for HTR Cover Creform from Adrian |  | NO-CHANGE |  | DUQUETTE | REPRIORITIZE AS C.I. ITEM | 5
2006-09-20 | 13 | N | 030 - MARK UP PRINTS FOR PARALLEL PVA'S |  | NO-CHANGE |  | GLASER |  | 5
2006-10-16 | 2 | Y | 040 - UNIT RELEASED AT 040 AND ROLLED TO ATC BLOCKS LIGHT CURTAIN. ADD SENSOR WITH FIELD WIREABLE CONNECTOR |  | INCREASE |  | BENDER | NEEDS FIELD WIREABLE CONNECTOR AND SENSOR SIMILAR TO PERFECT PROX | 5
2006-10-17 | 1 | N | 050 - SCREW GUN INTERNAL WIRING - DOES NOT SHOW FWD & REV |  | NO-CHANGE |  | DUQUETTE | USED PORT #2 - PORT #1 BAD | 5
2006-08-21 | 80 | N | GENERAL -ROUND CORNERS OF DUPLEX BOXES |  | NO-CHANGE |  | BENDER | TBD | CONTROLS
2006-09-28 | 1 | N | PC - PLANT ETHERNET TAG |  | NO-CHANGE |  | BENDER | BRAD IT | CONTROLS
2006-09-06 | 2 | N | 010 - STOP BUMPERS FOR MOVING SCREW COVER |  | NO-CHANGE |  | BENDER |  | MECHANICAL
2006-07-14 | 3 | N | 010 - USE SHOULDER BOLT FOR SLIDING SCREW COVER |  | NO-CHANGE |  | DUQUETTE | TBD | MECHANICAL

## EXAMPLE KTM
T/E NAME: | PACK SYSTEM
T/E #: | 4009670.001
DATE: | 7/1/2008 (UPDATED 7/1/08)
PROJECT: | PACK SYSTEM
SUPPLIER: | HOHL - R.MILAZZO
PROJECT ENGINEER: | T.GLASER
|  |  |  | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
| LINE ITEM DESCRIPTION | REF. | RESPONSIBLE | 2008-05-16 | 2008-05-23 | 2008-05-30 | 2008-06-06 | 2008-06-13 | 2008-06-20 | 2008-06-27 | 2008-07-04 | 2008-07-11 | 2008-07-18 | 2008-07-25 | 2008-08-01 | 2008-08-08 | 2008-08-15 | 2008-08-22 | 2008-08-29 | 2008-09-05 | 2008-09-12 | 2008-09-19 | 2008-09-26 | 2008-10-03 | 2008-10-10 | 2008-10-17 | 2008-10-24 | 2008-10-31 | 2008-11-07 | 2008-11-14 | 2008-11-21 | 2008-11-28 | 2008-12-05 | 2008-12-12 | PLANNED START | PLANNED FINISH | ACTUAL START DATE | CURRENT DUE DATE | COMMENTS
| PRODUCT DATA |  | DELPHI | [31 empty] | 2008-07-02 | 2008-07-03 | 2008-07-02 | 2008-07-03 | bar: 2008-07-04
| SPECIFICATION |  | DELPHI | [31 empty] | 2008-05-12 | 2008-05-30 | 2008-05-14 | 2008-05-30 | COMPLETE | bar: 2008-05-16 to 2008-05-30
| RFQ |  | DELPHI | [31 empty] | 2008-06-02 | 2008-06-13 | 2008-05-30 | 2008-06-11 | COMPLETE | bar: 2008-06-06 to 2008-06-13
| PR |  | DELPHI | [31 empty] | 2008-06-16 | 2008-06-20 | 2008-06-20 | 2008-06-20 | COMPLETE | bar: 2008-06-20
| PO |  | DELPHI | [31 empty] | 2008-06-23 | 2008-06-27 | 2008-06-26 | 2008-06-26 | COMPLETE | bar: 2008-06-27
| SAMPLE PARTS |  | DELPHI | [31 empty] | 2008-07-01 | 2008-07-04 | 2008-07-02 | 2008-07-03 | TO BE SHIPPED 7/3 | bar: 2008-07-04
| KICK OFF |  | SUPPLIER | [31 empty] | 2008-07-01 | 2008-07-04 |  | 2008-07-04 | bar: 2008-07-04
| DESIGN MECHANICAL |  | SUPPLIER | [31 empty] | 2008-06-23 | 2008-07-18 |  | 2008-07-18 | bar: 2008-06-27 to 2008-07-18
| DESIGN ELECTRICAL |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-11 to 2008-07-18
| DESIGN PNEUMATICS |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-11 to 2008-07-18
| RISK ASSESSMENT |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-11 |  | 2008-07-11 | bar: 2008-07-11
| CONCEPT APPROVAL (PEER, SAFETY, ERGO, TRADES) |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-11 |  | 2008-07-11 | bar: 2008-07-11
| MODEL / PLAN APPROVAL |  | SUPPLIER | [31 empty] | 2008-07-14 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-18
| DETAIL MECHANICAL APPROVAL |  | SUPPLIER | [31 empty] | 2008-07-14 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-18
| CONTROLS APPROVAL |  | SUPPLIER | [31 empty] | 2008-07-14 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-18
| PROCURE MECHANICAL |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-01 |  | 2008-08-01 | bar: 2008-07-25 to 2008-08-01
| PROCURE ELECTRICAL |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-01 |  | 2008-08-01 | bar: 2008-07-25 to 2008-08-01
| PROCURE PNEUMATICS |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-01 |  | 2008-08-01 | bar: 2008-07-25 to 2008-08-01
| MANUFACTURE PARTS |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-15 |  | 2008-08-15 | bar: 2008-07-25 to 2008-08-15
| CONTROLS ASSEMBLY |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-08 |  | 2008-08-08 | bar: 2008-07-25 to 2008-08-08
| FINAL ASSEMBLY |  | SUPPLIER | [31 empty] | 2008-08-04 | 2008-08-15 |  | 2008-08-15 | bar: 2008-08-08 to 2008-08-15
| DEBUG MECHANICAL & RING OUT |  | SUPPLIER | [31 empty] | 2008-08-18 | 2008-08-22 |  | 2008-08-22 | bar: 2008-08-22
| PROCURE RUN OFF PARTS |  | DELPHI | [31 empty] | 2008-07-21 | 2008-08-08 | 2008-07-02 | 2008-08-08 | bar: 2008-07-25 to 2008-08-08
| LOAD PROGRAM & DEBUG SYSTEM |  | DELPHI | [31 empty] | 2008-08-18 | 2008-08-22 |  | 2008-08-22 | bar: 2008-08-22
| QUALIFICATION (MSA, PEER, SAFETY, ERGO, TRADES) |  | DELPHI | [31 empty] | 2008-08-25 | 2008-09-12 |  | 2008-09-12 | bar: 2008-08-29 to 2008-09-12
| SHIP |  | SUPPLIER | [31 empty] | 2008-09-08 | 2008-09-12 |  | 2008-09-12 | bar: 2008-09-12
| INSTALLATION |  | DELPHI | [31 empty] | 2008-09-12 | 2008-09-19 |  | 2008-09-19 | bar: 2008-09-19
| QUALIFICATION |  | DELPHI | [31 empty] | 2008-09-19 | 2008-09-26 |  | 2008-09-26 | bar: 2008-09-26
DATE: | 7/1/2008 (UPDATED 7/1/508)
PROJECT: | PACK SYSTEM
SUPPLIER: | HOHL - R.MILAZZO
PROJECT ENGINEER: | T.GLASER
|  |  |  | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
| LINE ITEM DESCRIPTION | REF. | RESPONSIBLE | 2008-05-16 | 2008-05-23 | 2008-05-30 | 2008-06-06 | 2008-06-13 | 2008-06-20 | 2008-06-27 | 2008-07-04 | 2008-07-11 | 2008-07-18 | 2008-07-25 | 2008-08-01 | 2008-08-08 | 2008-08-15 | 2008-08-22 | 2008-08-29 | 2008-09-05 | 2008-09-12 | 2008-09-19 | 2008-09-26 | 2008-10-03 | 2008-10-10 | 2008-10-17 | 2008-10-24 | 2008-10-31 | 2008-11-07 | 2008-11-14 | 2008-11-21 | 2008-11-28 | 2008-12-05 | 2008-12-12 | PLANNED START | PLANNED FINISH | ACTUAL START DATE | CURRENT DUE DATE | COMMENTS
| PRODUCT DATA |  | DELPHI | [31 empty] | 2008-07-02 | 2008-07-03 | 2008-07-02 | 2008-07-03 | bar: 2008-07-04
| SPECIFICATION |  | DELPHI | [31 empty] | 2008-05-12 | 2008-05-30 | 2008-05-14 | 2008-05-30 | COMPLETE | bar: 2008-05-16 to 2008-05-30
| RFQ |  | DELPHI | [31 empty] | 2008-06-02 | 2008-06-13 | 2008-05-30 | 2008-06-11 | COMPLETE | bar: 2008-06-06 to 2008-06-13
| PR |  | DELPHI | [31 empty] | 2008-06-16 | 2008-06-20 | 2008-06-20 | 2008-06-20 | COMPLETE | bar: 2008-06-20
| PO |  | DELPHI | [31 empty] | 2008-06-23 | 2008-06-27 | 2008-06-26 | 2008-06-26 | COMPLETE | bar: 2008-06-27
| SAMPLE PARTS |  | DELPHI | [31 empty] | 2008-07-01 | 2008-07-04 | 2008-07-02 | 2008-07-03 | TO BE SHIPPED 7/3 | bar: 2008-07-04
| KICK OFF |  | SUPPLIER | [31 empty] | 2008-07-01 | 2008-07-04 |  | 2008-07-04 | bar: 2008-07-04
| DESIGN MECHANICAL |  | SUPPLIER | [31 empty] | 2008-06-23 | 2008-07-18 |  | 2008-07-18 | bar: 2008-06-27 to 2008-07-18
| DESIGN ELECTRICAL |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-11 to 2008-07-18
| DESIGN PNEUMATICS |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-11 to 2008-07-18
| RISK ASSESSMENT |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-11 |  | 2008-07-11 | bar: 2008-07-11
| CONCEPT APPROVAL (PEER, SAFETY, ERGO, TRADES) |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-11 |  | 2008-07-11 | bar: 2008-07-11
| MODEL / PLAN APPROVAL |  | SUPPLIER | [31 empty] | 2008-07-14 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-18
| DETAIL MECHANICAL APPROVAL |  | SUPPLIER | [31 empty] | 2008-07-14 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-18
| CONTROLS APPROVAL |  | SUPPLIER | [31 empty] | 2008-07-14 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-18
| PROCURE MECHANICAL |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-01 |  | 2008-08-01 | bar: 2008-07-25 to 2008-08-01
| PROCURE ELECTRICAL |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-01 |  | 2008-08-01 | bar: 2008-07-25 to 2008-08-01
| PROCURE PNEUMATICS |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-01 |  | 2008-08-01 | bar: 2008-07-25 to 2008-08-01
| MANUFACTURE PARTS |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-15 |  | 2008-08-15 | bar: 2008-07-25 to 2008-08-15
| CONTROLS ASSEMBLY |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-08 |  | 2008-08-08 | bar: 2008-07-25 to 2008-08-08
| FINAL ASSEMBLY |  | SUPPLIER | [31 empty] | 2008-08-04 | 2008-08-15 |  | 2008-08-15 | bar: 2008-08-08 to 2008-08-15
| DEBUG MECHANICAL & RING OUT |  | SUPPLIER | [31 empty] | 2008-08-18 | 2008-08-22 |  | 2008-08-22 | bar: 2008-08-22
| PROCURE RUN OFF PARTS |  | DELPHI | [31 empty] | 2008-07-21 | 2008-08-08 | 2008-07-02 | 2008-08-08 | bar: 2008-07-25 to 2008-08-08
| LOAD PROGRAM & DEBUG SYSTEM |  | DELPHI | [31 empty] | 2008-08-18 | 2008-08-22 |  | 2008-08-22 | bar: 2008-08-22
| QUALIFICATION (MSA, PEER, SAFETY, ERGO, TRADES) |  | DELPHI | [31 empty] | 2008-08-25 | 2008-09-12 |  | 2008-09-12 | bar: 2008-08-29 to 2008-09-12
| SHIP |  | SUPPLIER | [31 empty] | 2008-09-08 | 2008-09-12 |  | 2008-09-12 | bar: 2008-09-12
| INSTALLATION |  | DELPHI | [31 empty] | 2008-09-12 | 2008-09-19 |  | 2008-09-19 | bar: 2008-09-19
| QUALIFICATION |  | DELPHI | [31 empty] | 2008-09-19 | 2008-09-26 |  | 2008-09-26 | bar: 2008-09-26

## BLANK ITEM
T/E NAME:
T/E #:
PURCHASE TRACKING
DATE WRITTEN | PR # | I/O # | ITEM (INCLUDE QTY IF MULTIPLE) | AMOUNT | PO # | DATE ISSUED | SUPPLIER | STATUS | COMMENTS | INVOICE # | INVOICE APP'D DATE
MM/DD/YY | ##### | ### ### ### | AAAAAAAAAA | $#,###,###.## | ### ### ### | MM/DD/YY | AAAAAAAAAA | AAAAAAAAAA | AAAAAAAAAA | AAAAAAA | MM/DD/YY
TOTAL |  |  |  | 0
TIMING TRACKING
| QUOTED TIMING | DATE | DATE | DATE | DATE | DATE | DATE | DATE | DATE
PRODUCT DATA | MM/DD/YY | MM/DD/YY | MM/DD/YY | MM/DD/YY | MM/DD/YY | MM/DD/YY | MM/DD/YY | MM/DD/YY | MM/DD/YY
SPECIFICATION
RFQ
PR
PO
SAMPLE PARTS
KICK OFF
DESIGN MECHANICAL
DESIGN ELECTRICAL
DESIGN PNEUMATICS
RISK ASSESSMENT
CONCEPT APPROVAL
MODEL / PLAN APPROVAL
DETAIL MECHANICAL APPROVAL
CONTROLS APPROVAL
PROCURE MECHANICAL
PROCURE ELECTRICAL
PROCURE PNEUMATICS
MANUFACTURE PARTS
CONTROLS ASSEMBLY
FINAL ASSEMBLY
DEBUG MECHANICAL & RING OUT
PROCURE RUN OFF PARTS
LOAD PROGRAM & DEBUG SYSTEM
QUALIFICATION
SHIP
INSTALLATION
QUALIFICATION
HISTORY & CHANGE TRACKING
|  | Priority | 0 | 1 | 2 | 3 | 4 | CONTROLS, MECHANICAL, OR 5 IF DOCUMENTS VERIFIED
|  | Meaning | Safety | No Build Production / Quality Issue | Hinders Production But Does Not Stop It / Minor Quality Issue | General Working Environment | Continuous Improvement | Complete
DATE ADDED | ITEM | QUOTE REQUIRED (Y/N)? | DESCRIPTION | AMOUNT | PO EFFECT (INCREASE, DECREASE, NO-CHANGE) | DELPHI ACCEPTED? (Y/N) | RESPONSIBLE | STATUS | PRIORITY
MM/DD/YY | ### | A | AAAAAAAAAA | $#,###,###.## | AAAAAAAAAA | A | AAAAAAAAAA | AAAAAAAAAA | AAAAAAAAAA
COMPLETE

## BLANK KTM
T/E NAME: | PACK SYSTEM
T/E #: | 4009670.001
DATE: | 7/1/2008 (UPDATED 7/1/08)
PROJECT: | PACK SYSTEM
SUPPLIER: | HOHL - R.MILAZZO
PROJECT ENGINEER: | T.GLASER
|  |  |  | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
| LINE ITEM DESCRIPTION | REF. | RESPONSIBLE | 2008-05-16 | 2008-05-23 | 2008-05-30 | 2008-06-06 | 2008-06-13 | 2008-06-20 | 2008-06-27 | 2008-07-04 | 2008-07-11 | 2008-07-18 | 2008-07-25 | 2008-08-01 | 2008-08-08 | 2008-08-15 | 2008-08-22 | 2008-08-29 | 2008-09-05 | 2008-09-12 | 2008-09-19 | 2008-09-26 | 2008-10-03 | 2008-10-10 | 2008-10-17 | 2008-10-24 | 2008-10-31 | 2008-11-07 | 2008-11-14 | 2008-11-21 | 2008-11-28 | 2008-12-05 | 2008-12-12 | PLANNED START | PLANNED FINISH | ACTUAL START DATE | CURRENT DUE DATE | COMMENTS
| PRODUCT DATA |  | DELPHI | [31 empty] | 2008-07-02 | 2008-07-03 | 2008-07-02 | 2008-07-03 | bar: 2008-07-04
| SPECIFICATION |  | DELPHI | [31 empty] | 2008-05-12 | 2008-05-30 | 2008-05-14 | 2008-05-30 | COMPLETE | bar: 2008-05-16 to 2008-05-30
| RFQ |  | DELPHI | [31 empty] | 2008-06-02 | 2008-06-13 | 2008-05-30 | 2008-06-11 | COMPLETE | bar: 2008-06-06 to 2008-06-13
| PR |  | DELPHI | [31 empty] | 2008-06-16 | 2008-06-20 | 2008-06-20 | 2008-06-20 | COMPLETE | bar: 2008-06-20
| PO |  | DELPHI | [31 empty] | 2008-06-23 | 2008-06-27 | 2008-06-26 | 2008-06-26 | COMPLETE | bar: 2008-06-27
| SAMPLE PARTS |  | DELPHI | [31 empty] | 2008-07-01 | 2008-07-04 | 2008-07-02 | 2008-07-03 | TO BE SHIPPED 7/3 | bar: 2008-07-04
| KICK OFF |  | SUPPLIER | [31 empty] | 2008-07-01 | 2008-07-04 |  | 2008-07-04 | bar: 2008-07-04
| DESIGN MECHANICAL |  | SUPPLIER | [31 empty] | 2008-06-23 | 2008-07-18 |  | 2008-07-18 | bar: 2008-06-27 to 2008-07-18
| DESIGN ELECTRICAL |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-11 to 2008-07-18
| DESIGN PNEUMATICS |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-11 to 2008-07-18
| RISK ASSESSMENT |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-11 |  | 2008-07-11 | bar: 2008-07-11
| CONCEPT APPROVAL (PEER, SAFETY, ERGO, TRADES) |  | SUPPLIER | [31 empty] | 2008-07-07 | 2008-07-11 |  | 2008-07-11 | bar: 2008-07-11
| MODEL / PLAN APPROVAL |  | SUPPLIER | [31 empty] | 2008-07-14 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-18
| DETAIL MECHANICAL APPROVAL |  | SUPPLIER | [31 empty] | 2008-07-14 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-18
| CONTROLS APPROVAL |  | SUPPLIER | [31 empty] | 2008-07-14 | 2008-07-18 |  | 2008-07-18 | bar: 2008-07-18
| PROCURE MECHANICAL |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-01 |  | 2008-08-01 | bar: 2008-07-25 to 2008-08-01
| PROCURE ELECTRICAL |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-01 |  | 2008-08-01 | bar: 2008-07-25 to 2008-08-01
| PROCURE PNEUMATICS |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-01 |  | 2008-08-01 | bar: 2008-07-25 to 2008-08-01
| MANUFACTURE PARTS |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-15 |  | 2008-08-15 | bar: 2008-07-25 to 2008-08-15
| CONTROLS ASSEMBLY |  | SUPPLIER | [31 empty] | 2008-07-21 | 2008-08-08 |  | 2008-08-08 | bar: 2008-07-25 to 2008-08-08
| FINAL ASSEMBLY |  | SUPPLIER | [31 empty] | 2008-08-04 | 2008-08-15 |  | 2008-08-15 | bar: 2008-08-08 to 2008-08-15
| DEBUG MECHANICAL & RING OUT |  | SUPPLIER | [31 empty] | 2008-08-18 | 2008-08-22 |  | 2008-08-22 | bar: 2008-08-22
| PROCURE RUN OFF PARTS |  | DELPHI | [31 empty] | 2008-07-21 | 2008-08-08 | 2008-07-02 | 2008-08-08 | bar: 2008-07-25 to 2008-08-08
| LOAD PROGRAM & DEBUG SYSTEM |  | DELPHI | [31 empty] | 2008-08-18 | 2008-08-22 |  | 2008-08-22 | bar: 2008-08-22
| QUALIFICATION (MSA, PEER, SAFETY, ERGO, TRADES) |  | DELPHI | [31 empty] | 2008-08-25 | 2008-09-12 |  | 2008-09-12 | bar: 2008-08-29 to 2008-09-12
| SHIP |  | SUPPLIER | [31 empty] | 2008-09-08 | 2008-09-12 |  | 2008-09-12 | bar: 2008-09-12
| INSTALLATION |  | DELPHI | [31 empty] | 2008-09-12 | 2008-09-19 |  | 2008-09-19 | bar: 2008-09-19
| QUALIFICATION |  | DELPHI | [31 empty] | 2008-09-19 | 2008-09-26 |  | 2008-09-26 | bar: 2008-09-26